## Statement
0
Project Statement
Please enter project information below. Information entered here will automatically update all the worksheets in this file.
Project Title:
Project Sponsor:
Project Manager:
Include an action and an end result (performance), a target completion date (time), and an overall project budget (cost)
Project Statement:
Created on:
Last updated on:
| Language: |  | English
| English |  | chosen language: | 0
Dutch
French
German
Italian
Spanish
-
-
View License

## Objectives
0
Project Objectives
| Last updated on: |  | 0
| Project Title: |  | 0
| Project Manager: |  | 0
| Project Statement: |  | 0
| Develop Objectives |  |  | Identify Measures | Set Standards
| What value should this project produce? |  |  | How will the objectives be measured? | What is the minimum and/or target level of
| What short- and long-term benefits do we want? |  |  | 0 | performance?
| What constraints, restrictions, or resource limitations do we face? |  |  | 0 | 0
What imperatives must we respect?
| Objectives |  |  | Measures | Standards
At the end of this project, we will have achieved the following:

## WBS_RR
0
|  | Work Breakdown Structure |  |  |  |  | Resource Requirements
| Last updated on: |  | 0
| Project Title: |  | 0
| Project Manager: |  | 0
| Project Statement: |  | 0
| Develop Work Breakdown Structure |  |  | Identify Resource Requirements
| What are the major outputs of this project? |  | What work needs to be done to achieve the objectives? | What knowledge and skills are needed? | [5 empty] | What equipment is required? | [5 empty] | What special or unusual resources are needed?
| What are the components of each output? |  | How should work be organized to ease planning and | What facilities are needed? | [5 empty] | What supplies or materials will be used?
| 0 |  | control? | Knowledge/Skills |  |  |  | Facilities |  |  |  | Equipment |  |  |  | Materials |  |  |  | Special Resources
| WBS code |  | Work Breakdown Structure | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Total | Notes
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
* When entering WBS codes, apply style to each cell to format the indent (click format, style, style name dropdown, select 1, 1.1, 1.1.1, etc.)
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0

## RAM
0
|  | Work Breakdown Structure |  |  | Responsibility Assigment Matrix
| Last updated on: |  | 0
| Project Title: |  | 0 | Assign Responsibility
| Project Manager: |  | 0 | Who has resources for this work package? |  | Whose commitment is needed?
| Project Statement: |  | 0 | Who has knowledge, skills and experience? |  | Who will have primary responsibility for each work package?
0
People/Departments
| WBS code |  | Develop Work Breakdown Structure
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0

## CPM
0
|  | Work Breakdown Structure |  |  | Sequence and Schedule Deliverables
| Last updated on: |  | 0
| Project Title: |  | 0
| Project Manager: |  | 0 | Critical Path Method (CPM) |  |  |  |  | Sequence Deliverables (in days) |  |  |  |  | Schedule Deliverables (in calendar time)
| Project Statement: |  | 0
[8 empty] | Critical | Earliest |  | Latest |  |  | Planned |  | Actual
| WBS code |  | Develop Work Breakdown Structure | Precedence |  | Duration |  | Path? | Start | Finish* | Start** | Finish | Slack *** | Start | Finish | Start | Finish | Notes
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
| 0 |  | 0 | [6 empty] | 0 | 0 |  | 0
|  |  |  | * Earliest Finish = Earliest Start + Duration | [5 empty] | *** Slack = Latest Finish – Earliest Finish
** Latest Start = Latest finish – Duration
√

## Network
0
|  | Work Breakdown Structure |  |  | Network Diagram
| Last updated on: |  | 0
| Project Title: |  | 0
| Project Manager: |  | 0 | Sequence Deliverables
| Project Statement: |  | 0 | In what order must work packages be completed?
What knowledge, experience, templates, or historical information exists?
How much elapsed time will each work package take given the type and availability of resources?
| WBS code |  | Develop Work Breakdown Structure | Precedence | Duration | Network Diagram
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0

## Gantt
0
|  | Work Breakdown Structure |  |  | Gantt Chart
| Last updated on: |  | 0 | Schedule deliverables
| Project Title: |  | 0
| Project Manager: |  | 0 | What assumptions are being made about working time, resource availability, or other constraints?
| Project Statement: |  | 0 | When should work packages start and finish in calendar time?
[7 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
| WBS code |  | Develop Work Breakdown Structure | Precedence |  | Duration | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0

## PPA
0
|  | Work Breakdown Structure |  |  | Potential Problem Analysis (PPA)
| Last updated on: |  | 0
| Project Title: |  | 0 | Protect the Plan
| Project Manager: |  | 0 | Where is time, cost, performance most at risk? |  |  |  |  | What will be the impact of this potential problem (seriousness)? |  |  | How can we minimize the impact?
| Project Statement: |  | 0 | What could go wrong with this work package? |  |  |  |  | What could cause this potential problem? |  |  | How will we know the potential problem has occurred?
|  |  |  | What is the likelihood of this potential problem occurring (probability)? |  |  |  |  | How can we keep this likely cause from happening? |  |  | 0
| WBS code |  | Develop Work Breakdown Structure | List Potential Problems |  | P* | S** | Identify Likely Causes | Take Preventive Action | Plan Contingent Action | Identify Triggers | Steps/Modifications to the Plan | Who | When
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
*P = Probability **S = Seriousness

## POA
0
|  | Work Breakdown Structure |  |  | Potential Opportunity Analysis (POA)
| Last updated on: |  | 0
| Project Title: |  | 0 | Enhance the Plan
| Project Manager: |  | 0 | Where are there significant opportunities to impact time, cost, and performance? |  |  |  |  | What will be the impact of this potential opportunity (benefit)? |  |  | How can we maximize the benefit?
| Project Statement: |  | 0 | What could go better than expected with this work package? |  |  |  |  | What could cause this potential opportunity? |  |  | How will we know the potential opportunity has occurred?
|  |  |  | What is the likelihood of this potential opportunity occurring (probability)? |  |  |  |  | How can we increase the chance the potential opportunity will happen? |  |  | 0
| WBS code |  | Develop Work Breakdown Structure | List Potential Opportunities |  | P* | B** | Identify Likely Causes | Take Promoting Action | Plan Capitalizing Action | Identify Triggers | Steps/Modifications to the Plan | Who | When
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
*P = Probability **B = Benefit

## Implementation
0 |  |  | Start to Implement Checklist
;
| Last updated on: |  | 0
| Project Title: |  | 0
| Project Manager: |  | 0
| Project Statement: |  | 0
Start to Implement Checklist
|  | Individual and/or group communications planned |  | Team and team member performance systems agreed to and in place
|  | Project documentation assembled to guide implementation |  | Monitoring systems and methods agreed to and in place
|  | Materials, facilities, equipment, funding, etc., in place for initial tasks |  | Issue resolution protocols agreed to and in place
|  | Ground rules established for team interaction, communication |  | Reporting systems and methods agreed to and in place
|  | Potential Problem/Opportunity Analysis done for critical initial tasks |  | Change control systems agreed to and in place
| What type of formal project kickoff meeting is required? |  |  | Are specific policies or protocols for changes required?
| What other communication about the initiation of work might be required or useful? |  |  | What type of virtual or office space is required?
| What documentation might be useful or necessary during any kickoff communications? |  |  | What else?
What ground rules will be necessary for the entire team, or subgroups of the team, to operate efficiently?

## Change Auth.
0
Changes to the Project
Modifikationen der Projektplanung
;
| Last updated on: |  | 0
| Project Title: |  | 0
| Project Manager: |  | 0
| Project Statement: |  | 0
Change Authorization Number:
| Submitted by: |  |  | Date:
| Authorized by: |  |  | Date:
| Change Description |  |  |  | Change Alternatives Considered
| Change Impact |  |  |  | Anticipated Problems, Implications, Resolution

## Closeout
0
Closeout and Evaluate
;
| Last updated on: |  | 0
| Project Title: |  | 0
| Project Manager: |  | 0
| Project Statement: |  | 0
Closeout and Evaluate Checklist
|  | Deliverables all completed |  | Team members recognized
|  | Contingent actions disabled |  | Owners, sponsors, vendors notified of close
|  | Capitalizing actions disabled |  | Results documented
|  | Project accounts closed |  | Documents archived
Summarize the Project
| Did the project satisfy the project statement? If not, explain why. |  |  | How well did the team work together? How were performance expectations set and maintained?
| How well were project objectives satisfied? How well were customers sponsors, and end users satisfied with the project? If any objectives were not met, explain why. |  |  | How well were performance expectations satisfied during the project?
What, if any, changes were made to project definition after implementation started? Why?
How well did the project stay on schedule? If any major deliverables were early or late, explain why. How well did the team adjust to schedule changes?
What, if any, changes were made to the project plan after implementation started? Why?
How well were resources estimated overall? How did actual use of resources compare to the plan? How did changes in resource availability affect overall implementation?
How will you improve the next project you do?

## License
TEMPLATE LICENSE AGREEMENT
PLEASE READ THIS LICENSE CAREFULLY BEFORE USING THE KEPNER-TREGOE(R) TEMPLATES/WORKSHEETS (“TEMPLATES”). BY INSTALLING OR USING THE TEMPLATES YOU ARE AGREEING TO BE BOUND BY THE TERMS OF THIS LICENSE.
GENERAL. Except as authorized below, the Templates may not, in whole or in part, be used, copied, photocopied, printed, reproduced, translated or reduced to any electronic format or any medium of expression without prior written consent from Kepner-Tregoe, Inc. (“KT”).
LICENSE. KT hereby grants you a nonexclusive and nontransferable license to store the Templates in electronic form in place of or in addition to paper copies and to allow electronic access to and storage of completed forms in Microsoft(R) Excel format under the following terms and conditions:
1. You are not permitted to modify or alter the format of the Templates in any way without KT’s written permission.
2. This license is only granted to you if you have been trained in a KT approved program of Project Management and received a purchased set of KT Project Management workshop materials.
3. The KT copyright legend, namely © [year] Kepner-Tregoe, Inc. must remain on all screen and print copies of the Templates.
4. The Templates cannot be downloaded, transferred to or accessed by others unless such individuals agree to the terms of this License and are specifically eligible to use the Templates under Subsection 2 above.
5. The Templates shall not be used in conjunction with or as a part of any software that prompts the user to
complete the Templates.
TERMINATION. This License is effective until terminated. You may terminate this License at any time by destroying the Templates and all copies thereof. This License will terminate immediately without notice from KT if you fail to comply
with any provision of this License. Upon termination you must destroy all copies of the Templates.
GOVERNMENT END-USERS. If you are acquiring the Templates on behalf of any unit or agency of the United States Government, the following provisions apply. The Government agrees: (1) If the Templates are supplied to the Department of Defense (DoD), the Templates are classified as “Commercial Computer Software” and the Government is acquiring only “restricted rights” in the Templates as that term is defined in Clause 252.227-7013(c)(1) of the DFARS; and (2) If the Templates are supplied to any unit or agency of the United States Government other than DoD, the Government’s rights in the Templates will be as defined in Clause 52.227-19(c)(2) of the FAR or, in the case of NASA, in Clause 18-52.227-86(d) of the NASA Supplement to the FAR.
DISCLAIMER OF WARRANTY ON TEMPLATES. You expressly acknowledge and agree that use of the Templates is at your sole risk. The Templates are provided “AS IS” and without warranty of any kind and KT EXPRESSLY DISCLAIMS ALL WARRANTIES, EXPRESS AND IMPLIED, INCLUDING, BUT NOT LIMITED TO, THE IMPLIED WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR PURPOSE. FURTHERMORE, KT DOES NOT WARRANT OR MAKE ANY REPRESENTATIONS REGARDING THE USE OR THE RESULTS OF THE USE OF THE TEMPLATES IN TERMS OF THEIR CORRECTNESS, ACCURACY, RELIABILITY, CURRENTNESS, OR OTHERWISE. SOME JURISDICTIONS DO NOT ALLOW THE EXCLUSION OF IMPLIED WARRANTIES, SO THE ABOVE EXCLUSION MAY NOT APPLY TO YOU.
LIMITATION OF LIABILITY. UNDER NO CIRCUMSTANCES INCLUDING NEGLIGENCE, SHALL KT BE LIABLE TO YOU FOR ANY INCIDENTAL, INDIRECT, SPECIAL OR CONSEQUENTIAL ARISING OUT OF THE USE, MISUSE OR INABILITY TO USE THE TEMPLATES, EVEN IF KT OR KT’S AUTHORIZED REPRESENTATIVE HAS BEEN ADVISED OF THE POSSIBILITY OF SUCH DAMAGES. SOME JURISDICTIONS DO NOT ALLOW THE LIMITATION OR EXCLUSION OF LIABILITY FOR INCIDENTAL OR CONSEQUENTIAL DAMAGES, SO THE ABOVE LIMITATION OR EXCLUSION MAY NOT APPLY TO YOU.
CONTROLLING LAW AND SEVERABILITY. This License shall be governed by and construed in accordance with the laws of the United States and the State of New Jersey. If for any reason a court of competent jurisdiction finds any provision of this License or portion thereof, to be unenforceable, that provision of the License shall be enforced to the maximum extent permissible so as to effect the intent of the parties, and the remainder of this License shall continue in full force and effect.
COMPLETE AGREEMENT. This License constitutes the entire agreement between the parties with respect to the use of the Templates and supersedes all prior or contemporaneous understandings or agreements, written or oral, regarding such subject matter. No amendment to or modification of this License will be binding unless in writing and signed by a duly authorized representative of KT.
Project Statement Sheet

## Lexicon (hidden)
Lexicon
English | Dutch | French | German | Italian | Spanish | Hungarian | Czech
Statement | Omschrijving | Statement | Statement | Enunciato | Enunciado
Project Statement | Project Omschrijving | Enoncé du Projet | Projektbezeichnung | Enunciato | Enunciado
Please enter project information below. Information entered here will automatically update all the worksheets in this file. | Voer s.v.p. hieronder de project informatie in. Deze zal automatisch in alle worksheets verschijnen. |  |  |  | Registre aquí la información del proyecto. Toda información capturada en este espacio será repetida en las hojas succesivas.
Project Title: | Project Titel: | Titre du Projet | Projekt Name | Titolo del progetto | Nombre del proyecto
Project Sponsor: | Project Sponsor: | Sponsor de Projet | Projekt Sponsor | Sponsor del progetto | Patrocinador (Sponsor) del proyecto
Project Manager: | Project Manager: | Chef de Projet | Projekt Manager | Project Manager | Gerente (Líder) de Proyecto
Project Statement: | Project Omschrijving: | Enoncé du Projet | Projektbezeichnung: | Enunciato | Enunciado del Proyecto:
Include an action and an end result (performance), a target completion date (time), and an overall project budget (cost) | Voer een actie en eind resultaat (Performance), een einddatum (Tijd), en het project budget (Kosten) in. | Inclure un mot d'action et un résultat final (performance), une date d'achèvement cible (temps), et une estimation de prix (coût). | Schreiben Sie eine kurzes Statement, die Aktion und Endergebnis (Leistung), Zeit und Kosten (geplante) beinhaltet | Includere un'azione e un risultato finale (performance), una data limite per il completamento (tempo) e un budget complessivo (costi) | Incluir una acción y un resultado final (desempeño), una fecha límite para el término del proyecto (tiempo) y un presupuesto general del proyecto (costo).
Created on: | Aangemaakt op: | Created on: | Erstellt am: | Creato il: | Creado el (fecha):
Last updated on: | Laatste Update: | Last updated on: | Letzte Überarbeitung: | Last updated on: | Última versión:
Language: | Taal: | Language: | Sprache: | Language: | Idioma
Objectives | Doelstellingen | Objectifs du Projet | Zielsetzungen | Obiettivi | Objetivos
Project Objectives | Project doelstellingen | Objectifs du Projet | Projekt Zielsetzungen | Enunciato e Obiettivi | Objetivos del proyecto
Last updated on: | Laatste Update: | Date: | Letzte Überarbeitung: | Data: | Última versión:
Project Title: | Project Titel: | Titre du Projet | Projekt Name | Titolo del progetto | Título del proyecto:
Project Manager: | Project Manager: | Chef de Projet | Projekt Manager | Project Manager | Gerente de Proyecto
Project Statement: | Project Omschrijving: | Enoncé du Projet | Projektbezeichnung: | Enunciato | Enunciado del Proyecto
Develop Objectives | Ontwikkel Doelstellingen | Développer les Objectifs | Zielsetzungen entwickeln | Stabilire gli obiettivi | Desarrollar Objetivos
Identify Measures | Stel metingen vast | Identifier les Mesures | Messbarkeiten idendifiziert | Identificare le misure | Identificar Medidas
Set Standards | Bepaal grenswaarden | Etablir les Standards | Standards | Definire gli standard | Establecer Estándares
Measures | Metingen | Mesures | Messbarkeit | Misure | Medidas
Standards | Standaarden | Standards | Standards | Standard | Estándares
What value should this project produce? | Welke resultaten moeten gerealiseerd worden? | Quelle valeur ce projet doit-il apporter? | Was müssen wir fertigstellen? | Quale valore avremo ottenuto alla fine del progetto? | ¿Qué valor debería producir este proyecto?
What short- and long-term benefits do we want? | Welke korte en langetermijn voordelen willen we behalen? | Quels bénéfices, à court ou long terme, souhaitons-nous? | Welche Anforderungen müssen erfüllt werden? | Quali benefici a lungo e a breve desideriamo? | ¿Qué beneficios a corto y largo plazo necesitamos obtener?
What constraints, restrictions, or resource limitations do we face? | Met welke beperkingen, restricties of beperkte middelen zullen we te maken krijgen ? | A quelles contraintes devons-nous faire face? | Welche Einschränkungen müssen berücksichtigt werden? | Di quali vincoli, limitazioni di risorse doddiamo tener conto? | ¿Qué restricciones o limitaciones en recursos necesitamos respetar?
What imperatives must we respect? |  | Quels impératifs devons-nous respecter? |  | Quali condizioni dobbiamo soddisfare? | ¿Qué requisitos deben cumplirse?
At the end of this project, we will have achieved the following: | Aan het einde van het project hebben we: | A la fin du projet, nous aurons : | Am Ende des Projektes werden wir folgendes erreicht haben: | Alla fine del progetto avremo: | Al final del proyecto tendremos:
How will the objectives be measured? | Hoe gaan we meten of de doelstellingen gerealiseerd zijn? | Comment les objectifs seront-ils mesurés ? | Wie werden wir überprüfen/ messen, | Come gli obiettivi saranno misurati? | ¿Cómo mediremos los objetivos?
wie gut unser Projekt die Zielsetzung erfüllt?
What is the minimum and/or target level of | Wat is het minimum- en/of | Quel est le niveau de performance | Ab welchem Wert ist das Projekt erfolgreich? | Qual è il livello di performance minimo | ¿Cuál es el nivel mínino esperado de
performance? | het norm-niveau? | minimum et/ou cible ? |  | o desiderato? | desempeño?
WBS | WBS |  | WBS |  | EDT
Work Breakdown Structure | Work Breakdown Structure | Structure de Fractionnement des Tâches | Projectstrukturplan (PSP) | Work Breakdown Structure | Estructura de División del Trabajo
Project Objectives | Project doelstellingen | Objectifs du Projet | Projekt Zielsetzungen | Enunciato e Obiettivi | Objetivos del Proyecto
Last updated on: | Laatste Update: |  | Letzte Überarbeitung: |  | Última versión (fecha):
Project Title: | Project Titel: | Titre du Projet | Projekt Name | Titolo del progetto | Nombre del Proyecto:
Project Manager: | Project Manager: | Chef de Projet | Projekt Manager | Project Manager | Gerente de Proyecto:
Project Statement: | Project Omschrijving: | Enoncé du Projet | Projektbezeichnung: | Enunciato | Enunciado del Proyecto:
WBS code | WBS code | Code SFT | PSP Numerierung | Codice WBS | EDT
Develop Work Breakdown Structure | Ontwikkel Breakdown Structure | Développer la Structure de Fractionnement des Tâches | Entwickeln des Projektstrukturplans | Sviluppare la Work Breakdown Structure | Desarrollar la Estructura de División del Trabajo
* When entering WBS codes, apply style to each cell to format the indent (click format, style, style name dropdown, select 1, 1.1, 1.1.1, etc.) | * Bij het invoeren van WBS codes, pas op iedere cel de juiste stijl toe tbv inspringen: (klik format, style, style naam dropdown, kies 1, 1.1, 1.1.1, etc.) |  |  |  | *Al registrar los códigos de la EDT, aplique el estilo a cada celda para formatear la numeración (hacer click en formato, estilo, nombre del estilo, menú, escoja 1, 1.1, 1.1.1, etc.)
What are the major outputs of this project? | Wat zijn de belangrijkste resultaten van het project? | Quels sont les principaux résultats attendus | Was sind die Hauptaufgaben dieses Projektes? | Quali sono i principali risultati/output del progetto? | ¿Cuáles son las realizaciones mayores de este
What are the components of each output? | Welke componenten kunnen we hierin onderscheiden? | de ce projet ? | Was müssen wir bei diesem Projekt fertigstellen? | Quali sono le singole componenti di ogni output? | proyecto?
|  | Quels sont les composantes de… ? |  |  | ¿Cuáles son los componentes de cada realización?
What work needs to be done to achieve the objectives? | Hoe bereiken we elke project doelstelling? | Comment allons-nous atteindre cet objectif ? | Was müssen wir tun, um diese Zielsetzungen zu erfüllen? | Quali attività sono necessarie per raggiungere gli obiettivi? | ¿Qué trabajo necesita realizarse para satisfacer los objetivos?
How should work be organized to ease planning and | Hoe gaan we het werk organiseren om goed te kunnen | Comment allons-nous organiser le travail pour faciliter la | Wie werden wir das tun? | Come dovrebbero essere organizzate le attività per | ¿Cómo debiera estar organizado el trabajo para facilitar
control? | managen, monitoren en rapporteren? | planification et le contrôle ? |  | facilitare la pianificazione ed il controllo? | su planificación y control?
Resource Requirements | Benodigde Middelen | Besoins en Ressources | Ressourcenbedarf | Risorse necessarie | Recursos Requeridos
Identify Resource Requirements | Bepaal de benodigde middelen | Identifier les Besoins en Ressources | Ressourcenbedarf ermitteln | Determinare le risorse necessarie | Identificar los Recursos Requeridos
What knowledge and skills are needed? | Welke kennis en vaardigheden zijn nodig? | Quelles connaissances et compétences sont nécessaires? | Welche Kenntnisse und Fähigkeiten sind erforderlich? | Quali sono le capacità e le conoscenze necessarie? | ¿Qué conocimiento y habilidades se necesitan?
What facilities are needed? | Welke faciliteiten zijn nodig? | Quelles installations sont requises? | Welche besonderen Ressourcen benötigen wir? | Quali strutture servono? | ¿Qué instalaciones se necesitan?
What equipment is required? | Welke apparatuur is nodig? | Quel équipement est nécessaire? | Welche Ausrüstung, Räumlichkeiten oder Materialien | Quali attrezzature servono? | ¿Qué equipo se requiere?
What supplies or materials will be used? | Welke voorraden, en materialen zijn nodig? | Quels fournitures et matériels vont-être utilisés? | brauchen wir? | Quali materiali saranno usati? | ¿Qué suministros o materiales se usarán?
What special or unusual resources are needed? | Welke speciale of ongewone middelen zijn nodig? | Quelles sont les ressources spéciales ou inhabituelles requises? | Wieviel wird es kosten? | Quali risorse speciali o inusuali sono necessarie? | ¿Qué recursos especiales o poco comunes son necesarios?
Knowledge/Skills | Kennis/Vaardigheden | Connaissances/Compétences | Kenntnisse/Fähigkeiten | Conoscenze/capacità | Conocimiento/Habilidades
Facilities | Faciliteiten | Installations | Räumlichkeiten | Strutture | Facilidades
Equipment | Apparatuur | Equipement | Ausrüstung | Attrezzature | Equipo
Materials | Materialen | Materiel | Material | Materiali | Materiales
Special Resources | Bijzondere middelen | Ressources Spéciales | Besondere Ressourcen | Risorse speciali | Recursos Especiales
Type | Type | Type | Art | Tipo | Tipo
Amt | Aant | Montant | PT | Q | Cantidad
Unit Cost | Prijs p stuk | Coût unitaire | Kosten pro PT | Costo unitario | Costo Unitario
Total Cost | Totale kosten | Coût total | Kosten | Costo totale | Costo Total
Total | Totaal | Total | Summe | Totale | Total
Notes | Aantekeningen | Notes | Bemerkungen | Note | Notas
RAM | RAM | RAM | RAM | RAM | MAR
Responsibility Assigment Matrix | Verantwoordelijkheden Matrix | Grille de Partage des Responsabilités | Verantwortungsmatrix | Matrice compiti/responsabilità | Matriz de Asignación de Responsabilidad
Assign Responsibility | Wijs verantwoordelijkheden toe | Attribuer les Responsabilités | Verantwortung festlegen | Assegnare le responsabilità | Asignar Responsabilidad
People/Departments | Personen/afdelingen | Personnes/Départements | Personen/ Abteilungen | Persone/Reparti | Personas/Departamentos
Who has resources for this work package? | Wie heeft de middelen voor dit werkpakket? | Qui a les ressources pour ce work package ? | Wer verfügt über Ressourcen für dieses Endelement? | Chi possiede le conoscenze e le capacità per svolgere | ¿Quién tiene los recursos para este paquete de trabajo?
Who has knowledge, skills and experience? | Wie heeft de kennis, vaardigheden, ervaring? | Qui possède la connaissance, les compétences, et l'expérience ? | Wer hat Wissen und Erfahrung? | questo work package? | ¿Quién tiene el conocimiento, las habilidades y la experiencia para
|  |  |  | Chi ha le conoscenze, le capacità e l'esperienza necessarie? | este paquete de trabajo?
Whose commitment is needed? | Van wie is commitment nodig? | Qui doit-être impliqué ? | Wessen aktive Unterstützung wird benötigt? | Chi bisogna coinvolgere? | ¿Quiénes tienen el compromiso que se necesita para este paquete de trabajo?
Who will have primary responsibility for each work package? | Wie heeft de primaire verantwoordelijkheid voor elk werkpakket? | Qui a la responsabilité principale de chaque work package ? | Wer hat die primäre Verantwortung für jedes einzelne Arbeitspaket? | Chi sarà responsabile di ogni work package? | ¿Quién tendrá la responsabilidad primaria para realizar cada paquete de trabajo?
CPM | Kritische pad methode | CPM |  |  | CPM
Sequence and Schedule Deliverables | Bepaal volgorde en Maak tijdschema | Réseau d'Activités |  |  | Diagrama de Red
Critical Path Method (CPM) | Kritieke Pad Methode (CPM) |  |  |  | Método de Ruta Crítica (Critical Path Method CPM)
Sequence Deliverables (in days) | Bepaal volgorde (in dagen) |  |  |  | Establecer la Secuencia de las Realizaciones (en días)
Schedule Deliverables (in calendar time) | Maak tijdschema (in kalender) | Planifier les Livrables | Sequenza delle attività | Sequenza delle attività | Programar las Realizaciones (en tiempo calendario)
Precedence | Voorwaarde |  |  |  | Relaciones de Dependencia (después de)
Duration | Duur | Durée | Dauer | Durata | Duración (días)
Critical | Kritieke |  |  |  | ¿Camino
Path? | Pad? |  |  |  | Crítico?
Earliest | Vroegste |  |  |  | Inicio
Start | Start |  |  |  | Mínimo
Finish* | Finish* |  |  |  | Término
Latest | Laatste |  |  |  | Mínimo
Start** | Start** |  |  |  | Inicio
Finish | Finish |  |  |  | Máximo
Slack *** | Slack *** |  |  |  | Holgura
Planned | Geplande |  |  |  | Planeado
Start | Start |  |  |  | Inicio
Finish | Finish |  |  |  | Término
Actual | Werkelijke |  |  |  | Realizado
Start | Start |  |  |  | Inicio
Finish | Finish |  |  |  | Término
Notes | Aantekeningen |  |  |  | Notas
* Earliest Finish = Earliest Start + Duration | * Vroegste Finish = Vroegste Start + Duur |  |  |  | *Término Mínimo = Inicio Mínimo + Duración
** Latest Start = Latest finish – Duration | ** Laatste Start = Laatste Finish – Duur |  |  |  | **Inicio Máximo = Término Máximo- Duración
*** Slack = Latest Finish – Earliest Finish | *** Slack = Laatste Finish – Vroegste Finish |  |  |  | ***Holgura = Término Máximo - Inicio Mínimo
Network Diagram | Netwerk diagram | Réseau d'Activités | Netzplan Diagramm | Diagramma reticolare | Diagrama de Red
Sequence Deliverables | Bepaal volgorde waarin resultaten moet worden opgeleverd | Planifier les Livrables | Reihenfolge der Aufgaben bestimmen | Sequenza delle attività | Secuencia de las Realizaciones
In what order must work packages be completed? | In welke volgorde moeten de werkpakketten worden gerealiseerd? | Dans quel ordre les work packages doivent-ils être accomplis ? | In welcher Reihenfolge müssen Endelemente fertiggestellt werden? | Con che ordine devono essere completati i work package? | ¿En qué orden deben terminarse los paquetes de trabajo?
What knowledge, experience, templates, or historical information exists? | Welke kennis, ervaring, voorbeelden of historische informatie is er beschikbaar? | Quels sont les connaissances, expériences, modèles ou informations historiques existants ? | Welche kalendarische Dauer wird jedes Arbeitspaket benötigen (Ressourcenverfügbarkeit unterstellt)? | Quali sono le conoscenze, le esperienze, le informazioni a disposizione? | ¿Qué conocimiento, experiencias, formatos o información histórica existe?
How much elapsed time will each work package take given the type and availability of resources? | Hoeveel tijd is nodig voor ieder werkpakket, als we rekening houden met de kwaliteit en de beschikbaarheid van de middelen? | Combien de temps durera cette tâche, compte tenu des ressources et de leur disponibilité ? |  | Quanto tempo sarà necessario per completare ogni work package, in funzione del tipo e della disponibilità delle risorse necessarie? | ¿Cuánto tiempo requiere cada paquete de trabajo de acuerdo al tipo y a la disponibilidad de los recursos?
Precedence | afhankelijk van | Antériorité | abhängig von | Precedenza | Dependencia
Duration | doorlooptijd | Durée | kalend. Dauer | Durata | Duración
Network Diagram | Netwerk diagram | Réseau d'Activités | Netzplan Diagramm | Diagramma reticolare | Diagrama de red
Gantt Chart | Gantt | Tableau de Gantt | Gantt Chart | Diagramma di Gantt | Gráfica de Gantt
Gantt Chart | Gantt | Tableau de Gantt | Gantt Chart | Diagramma di Gantt | Gráfica de Gantt
Schedule deliverables | Maak tijdschema | Programmer les livrables | Aufgaben planen | Sequenza delle attività | Programar las Realizaciones
What assumptions are being made about working time, resource availability, or other constraints? | Welke aannames zijn gedaan m.b.t. datum, beschikbare middelen of andere beperkingen? | Quelles hypothèses existent concernant le temps de travail, la disponibilité des ressources, ou toute autre contrainte ? | Wie lange werden wir brauchen, um jedes einzelne Arbeitspaket fertigzustellen? | Quali supposizioni devono essere fatte sul tempo a disposizione per lavorare, sulle risorse o altri vincoli? | ¿Qué supuestos se están haciendo acerca del tiempo requerido para realizar el trabajo, sobre la disponibilidad de recursos o de otras restricciones?
When should work packages start and finish in calendar time? | Wanner beginnen en wanneer gereed (datum)? | A quel moment du calendrier les tâches devront-elles commencer et finir ? | An welchen Kalendertagen beginnt und endet jedes Arbeitspaket? | In che giorno i work package dovrebbe iniziare e finire sul calendario? | ¿Cuándo debieran iniciar y terminar los paquetes de trabajo de acuerdo a las fechas en el calendario?
Precedence | Voorwaarde | Antériorité | abhängig von | Precedenza | Dependencia
Duration | doorlooptijd | Durée | kalend. Dauer | Durata | Duración
M | M | L | M | L | L
T | D | M | D | M | M
W | W | M | M | M | M
T | D | J | D | G | J
F | V | V | F | V | V
Week 1 | Week 1 | Week 1 | Woche 1 | Week 1 | Semana 1
Week 2 | Week 2 | Week 2 | Woche 2 | Week 2 | Semana 2
Week 3 | Week 3 | Week 3 | Woche 3 | Week 3 | Semana 3
Week 4 | Week 4 | Week 4 | Woche 4 | Week 4 | Semana 4
Week 5 | Week 5 | Week 5 | Woche 5 | Week 5 | Semana 5
Week 6 | Week 6 | Week 6 | Woche 6 | Week 6 | Semana 6
Week 7 | Week 7 | Week 7 | Woche 7 | Week 7 | Semana 7
Week 8 | Week 8 | Week 8 | Woche 8 | Week 8 | Semana 8
Week 9 | Week 9 | Week 9 | Woche 9 | Week 9 | Semana 9
Week 10 | Week 10 | Week 10 | Woche 10 | Week 10 | Semana 10
Week 11 | Week 11 | Week 11 | Woche 11 | Week 11 | Semana 11
Week 12 | Week 12 | Week 12 | Woche 12 | Week 12 | Semana 12
PPA | PPA | APP | APP | APP | APP
Potential Problem Analysis (PPA) | Potentiële Problemen Analyse (PPA) | Analyse des Problèmes Potentiels (APP) | Analyse Potentieller Probleme (APP) | Analisi del problema potenziale (APP) | Análisis de Problemas Potenciales
Protect the Plan | Bescherm het Plan | Protéger le Plan | Plan absichern | Proteggere il piano | Proteger el Plan
Where is time, cost, performance most at risk? | Waar bevindt zich met betrekking tot de tijd, de kosten of het resultaat het grootste afbreukrisico? | Où sont les risques les plus importants en termes de temps, coûts et performance ? | Wo sind die grössten Risiken in Bezug auf Zeit, Kosten und Leistung? | Quali componenti elementari sono sul percorso critico? | ¿Dónde tienen mayor riesgo el tiempo, el desempeño y el costo del proyecto?
What could go wrong with this work package? | Wat zou er mis kunnen gaan met dit werkpakket? | A quelle éventualité négative peut-on s'attendre sur ce work package ? | Was könnte bei diesem Arbeitspaket schiefgehen? | Cosa potrebbe andar male? | ¿Qué podría salir mal con este paqiuete de trabajo?
What is the likelihood of this potential problem occurring (probability)? | Hoe groot is de kans dat dit potentiële probleem op zal treden (kans)? | Quelle est la probabilité que ce problème potentiel survienne ? | Wie groß ist die Wahrscheinlichkeit des Eintretens? | Qual è la probabilità che questo problema potenziale si verifichi? | ¿Cuál es la probabilidad de que este problema ocurra?
What will be the impact of this potential problem (seriousness)? | Wat zou het effect kunnen zijn van dit potentile probleem (ernst)? | Quel serait la gravité de ce problème potentiel ? | Wie groß wäre die Tragweite? | Quale sarà l'impatto? | ¿Cuál sería el impacto? (gravedad)
What could cause this potential problem? | Wat zou de oorzaak kunnen zijn van dit potentiële probleem? | Quelle pourrait être l'origine de ce problème ? | Was könnte dieses potentielle Problem verursachen? | Cosa potrebbe causare questo problema potenziale? | ¿Qué causas podrían ocasionar este problema?
How can we keep this likely cause from happening? | Hoe kunnen we voorkomen dat de meest waarschijnlijke oorzaak optreedt? | Comment pouvons-nous prévenir cette cause éventuelle ? | Wie können wir diese Ursache verhindern? | Come possiamo prevenire questa causa probabile? | ¿Cómo podemos evitar que este problema ocurra?
How can we minimize the impact? | Wat kan de gevolgen beperken als dit ons overkomt? | Que ferons-nous si ce problème potentiel survient ? | Wie können wir die Tragweite reduzieren, falls es doch dazu kommt? | Cosa faremo se questo si verifica? | ¿Cómo podemos minimizar el impacto?
How will we know the potential problem has occurred? | Hoe weten we of het potentiële probleem opgetreden is? | Comment saurons-nous que le problème potentiel est survenu ? | Wie werden wir erfahren, dass es zu diesem Problem gekommen ist? | Come faremo a sapere se si è verificato? | ¿Cómo sabremos que el problema potencial se está presentando?
List Potential Problems | Bepaal Potentiële Problemen | Liste des Problèmes Potentiels | Liste potentieller Probleme | Elenco dei problemi potenziali | Hacer una lista de los Problemas Potenciales
P* | W* | P* | W* | P* | P*
S** | E** | G** | T** | G** | G**
Identify Likely Causes | Bepaal waarschijnlijke oorzaken | Identifer les Causes Probables | Identifizierung mögl. Ursachen | Identificare cause probabili | Identificar Causas Posibles
Take Preventive Action | Neem preventieve maatregelen | Prendre des Mesures Préventives | vorbeugende Massnahmen | Adottare azioni preventive | Tomar Acción Preventiva
Plan Contingent Action | Plan gevolgbestrijdende maatregelen | Planifier les Mesures de Secours | Eventual-massnahmen | Prevedere azioni di soccorso | Panificar Acción Contingente
Identify Triggers | Bepaal Triggers | Identifier les Déclencheurs | Auslöser | Individuare allarmi | Identificar Disparadores
Steps/Modifications to the Plan | Stappen/Wijzigingen in het plan | Etapes/Modifications | nächste Schritte/ Modifizierung des Plans | Passi e/o cambiamenti del piano | Pasos/Modificaciones al Plan
Who | Wie | Qui | Wer? | Chi? | Quién
When | Wanneer | Quand | Bis Wann? | Quando? | Cuándo
*P = Probability **S = Seriousness | *W = Waarschijnlijkheid **E = Ernst | *P = Probabilité **G = Gravité | *W = Wahrscheinlichkeit **T = Tragweite | *P = Probabilità **G = Gravità | *P = Probabilidad **G = Gravedad
POA | POA | AOP | APC | AOP | AOP
Potential Opportunity Analysis (POA) | Potentiële Opportuniteiten Analyse (POA) | Analyse des Opportunités Potentielles (AOP) | Analyse Potentieller Chancen (APC) | Analisi dell'opportunità potenziale (AOP) | Análisis de Oportunidades Potenciales (AOP)
Enhance the Plan | Verbeter het plan | Renforcer le Plan | Chancen optimal nutzen | Migliorare il piano | Mejorar el Plan
Where are there significant opportunities to impact time, cost, and performance? | Waar zien we significante opportuniteiten? | Où sont les opportunités significatives ? | Wo sehen wir signifikante Chancen? | Dove ci sono delle opportunità potenziali? | ¿Cuáles son las oportunidades importantes para impactar el tiempo, el costo y el desempeño?
What could go better than expected with this work package? | Wat zou beter kunnen gaan dan verwacht? | A quelle éventualité positive peut-on s'attendre sur ce work package ? | Was könnte besser gehen als erwartet? | Cosa potrebbe andare meglio rispetto a quanto previsto? | ¿Qué podría salir mejor que lo esperado en este paquete de trabajo?
What is the likelihood of this potential opportunity occurring (probability)? | Wat is de waarschijnlijkheid dat deze potentiële opportuniteit op zal treden (kans)? | Quelle est la probabilité que cette opportunité potentielle survienne ? | Wie wahrscheinlich ist es, dass es zu dieser Chance kommt? | Qual è la probabilità che questa opportunità potenziale si verifichi? | ¿Cuál es la probabilidad que esta oportunidad ocurra?
What will be the impact of this potential opportunity (benefit)? | Wat zou het effect kunnen zijn van deze potentiële opportuniteit (voordeel)? | Quel serait le bénéfice de cette opportunité potentielle ? | Wie groß wäre der Nutzen? | Quali saranno i benefici? | ¿Cuál será el impacto de esta oportunidad potencial? (beneficio)
What could cause this potential opportunity? | Wat zou de oorzaak kunnen zijn van deze potentiële opportuniteit? | Quelle pourrait être l'origine de cette opportunité ? | Was sind mögliche Ursachen für diese Chance? | Cosa potrebbe causare questa opportunità potenziale? | ¿Qué podría causar esta oportunidad potencial?
How can we increase the chance the potential opportunity will happen? | Wat kunnen we doen om de kans vergroten dat deze oorzaak leidt tot de potentiële opportuniteit? | Comment pouvons-nous promouvoir cette cause éventuelle ? | Was können wir tun, um die Wahrscheinlichkeit zu erhöhen? | Come possiamo promuovere questa causa? | ¿Cómo podemos aumentar la probabilidad de que esta oportunidad potencial ocurra?
How can we maximize the benefit? | Wat gaan we doen als de potentiële opportuniteit optreedt? | Que ferons-nous si cette opportunité potentielle survient ? | Wie können wir die Chance optimal ausschöpfen? | Cosa faremo se questo si verifica? | ¿Cómo podemos aumentar el beneficio?
How will we know the potential opportunity has occurred? | Hoe weten we dat de potentiële opportuniteit opgetreden is? | Comment saurons-nous que l'opportunité potentielle est survenue ? | Wie werden wir erfahren, dass diese Chance eingetreten ist? | Come faremo a sapere se si è verificata? | ¿Cómo sabremos que la oportunidad potencial ha ocurrido?
List Potential Opportunities | Bepaal Potentiële Opportuniteiten | Liste des Opportunités Potentielles | Liste potentieller Chancen | Elenco delle opportunità potenziali | Hacer una Lista de Oportunidades Potenciales
P* | W* | P* | W* | P* | P*
B** | V** | B** | N** | B** | B**
Identify Likely Causes | Bepaal waarschijnlijke oorzaken | Identifier les Causes Probables | Identifizierung mögl. Ursachen | Identificare cause probabili | Identificar Causas Probables
Take Promoting Action | Neem stimulerende maatregelen | Prendre les Mesures de Promotion | fördernde Massnahmen | Adottare azioni promozionali | Tomar Acción Promotora
Plan Capitalizing Action | Plan gevolgbevorderende maatregelen | Prévoir les Mesures de Capitalisation | ausschöpfende Massnahmen | Prevedere azioni di capitalizzaz. | Panificar Acción Beneficiadora
Identify Triggers | Bepaal Triggers | Identifier les Déclencheurs | Auslöser | Individuare allarmi | Identificar Disparadores
Steps/Modifications to the Plan | Stappen/Wijzigingen in het plan | Etapes / Modifications | nächste Schritte/ Modifizierung des Plans | Passi e/o cambiamenti | Paos/Modificaciones al Plan
Who | Wie | Qui | Wer? | Chi? | Quién
When | Wanneer | Quand | Bis wann? | Quando? | Cuándo
*P = Probability **B = Benefit | *W = Waarschijnlijkheid **V = Voordeel | *P = Probabilité **B = Benefice | *W = Wahrscheinlichkeit **N = Nutzen | *P = Probabilità **B = Beneficio | *P = Probabilidad **B = Beneficio
Implement | Implementeer | Implement | Implementierung | Implement | Implementar
Start to Implement | Start de implementatie | Démarrer la Réalisation | Implementierung starten | Iniziare l'esecuzione | Iniciar la Implementación
Start to Implement Checklist | Checklist Start Implementatie | Check-list pour Démarrer la Réalisation | Checkliste, um mit der Implementierung zu starten | Checklist per iniziare l'esecuzione | Checklist para Iniciar la Implementación
Individual and/or group communications planned | Individuele en/of groeps communicatie gepland | Communication individuelle ou de groupe planifiée | Einzel- und Gruppenkommunikation geplant | Comunicazioni individuali e/o di gruppo pianificate | Se tienen planificadas las comunicaciones individuales y de grupo
Project documentation assembled to guide implementation | Projectdocumentatie samengesteld ten behoeve van implementatie | Documentation de projet utile à la réalisation réunie | Projekt-Dokumentation für Monotoring geeignet | Documentazione del progetto, per guidare l'esecuzione, realizzata | Se tiene integrada la documentación del proyecto como guía de implementación
Materials, facilities, equipment, funding, etc., in place for initial tasks | Materialen, faciliteiten, apparatuur, financiering, e.d. gereed voor eerste taken | Financements, matériels, installations, équipements prêts | Verfügbarkeit von Material, Räumlichkeiten und Ausrüstung sichergestellt | Materiali, attrezzature, locali, ecc..., pronti per le prime attività | Están listos y en su sitio los materiales, las instalaciones, el equipo, los recursos económicos, entre otros, para llevar a cabo las tareas iniciales
Ground rules established for team interaction, communication | Werkafspraken gemaakt voor interactie/communicatie van team | Règles de base pour les relations au sein de l'équipe et communication établies | Grundregeln für Teamwork und -kommunikation festgelegt | Regole di base definite | Se han establecido las reglas de juego para el trbajo en equipo y la comunicación
Potential Problem/Opportunity Analysis done for critical initial tasks | Potentiële Problemen / Opportuniteiten Analyse verricht voor essentiële eerste taken | APP/AOP faites pour les tâches critiques initiales | Risikobewertung für kritische Bereiche durchgeführt | APP e AOP per le attività crictiche eseguite | Se han realizado el Análisis de Problemas Potenciales / de Oportunidades Potenciales para las tareas iniciales clasificadas como críticas
Team and team member performance systems agreed to and in place | Performance systemen voor team en teamleden overeengekomen en gereed | Systèmes de performance de l'équipe et des membres de l'équipe approuvés et en place | Performance System überdacht und bei Aufgabenverteilung berücksichtigt | Performance system concordato e attivato | Se han acordado y están instalados los sistemas de desempeño del Equipo de Proyecto y sus miembros
Monitoring systems and methods agreed to and in place | Monitoring systemen en methoden overeengekomen en gereed | Systèmes de contrôle approuvés et en place | Monitoring Werkzeuge und Methoden vereinbart und bereit | Metodo e sistema di monitoraggio concordato e attivato | Se han acordado y están instalados los sistemas y métodos de monitoreo
Issue resolution protocols agreed to and in place | Issue resolution protocollen overeengekomen en gereed | Protocoles de résolution de problèmes approuvés | Problemlösungstools vereinbart und bereit | Protocolli di risoluzione dei problemi concordati e attivati | Se han acordado y están instalados los sistemas de resolución de preocupaciones para el proyecto
Reporting systems and methods agreed to and in place | Raportage systemen and methoden overeengekomen en gereed | Systèmes et méthodes de reporting approuvés et en place |  | Sistemi e metodi di reporting concordati e attivati | Se han acordado y están instalados los sistemas y métodos de reporte del proyecto
Change control systems agreed to and in place | Change control systemen overeengekomen en gereed | Systèmes du contrôle du changement approuvés et en place | Modifikationstools vereinbart und bereit | Sistemi per controllare i cambiamenti concordati e attivati | Se han acordado y están instalado los sistemas de control de cambios
What type of formal project kickoff meeting is required? | Welk type formele startbijeenkomst is noodzakelijk? | Une réunion de kick-off formelle est-elle nécessaire ? | Wie gestalten Sie den "Kick-Off" Ihres Projektes? | Che tipo di riunioni formali sono necessarie? | ¿Qué tipo de reunión de arranque se requiere?
What other communication about the initiation of work might be required or useful? | Welke andere communicatie over aanvang van de werkzaamheden is noodzakelijk of zinvol? | Quels sont les autres communications utiles ou nécessaires avant de commencer le travail ? | Welche weiteren Kommunikations-Tools sind für den Start Ihres Projektes sinnvoll? | Quali altre forme di comunicazione possono essere utili o necessarie all'inizio dell'esecuzione? | ¿Qué otras comunicaciones acerca del inicio del trabajo se pueden requerir o pueden ser útiles?
What documentation might be useful or necessary during any kickoff communications? | Welke documentatie is zinvol of noodzakelijk voor communicatie over de projectstart? | Quels sont les documents nécessaires ou utiles pour les communications de la réunion de kick-off ? | Welche Art der Dokumentation ist während des "Kick-Off"s sinnvoll? | Che tipo di documentazione può essere utile o necessaria durante le riunioni? | ¿Qué documentación puede ser útil o necesaria durante la comunicación de arranque del proyecto?
What ground rules will be necessary for the entire team, or subgroups of the team, to operate efficiently? | Welke werkafspraken zijn noodzakelijk om met het hele team of in groepen efficient te kunnen functioneren? | Quelles règles de base vont être nécessaires à l'équipe entière ainsi qu'aux sous-groupes de l'équipe ? | Welche Regeln und Dokumentationen sind für spätere Änderungen notwendig und sinnvoll? | Quali sono le regole necessarie per il gruppo, o i sottogruppi, per operare efficacemente? | ¿Qué reglas del juego serán necesarias para que el Equipo de proyecto o los subgrupos de proyecto operen eficientemente?
Are specific policies or protocols for changes required? | Zijn er specifieke richtlijnen of protocollen voor verandering nodig? | Des politiques ou protocoles de changements sont-ils nécessaires ? |  | Sono previsti dei protocolli o delle azioni particolari in caso siano necessarie delle modifiche? | ¿Se requieren políticas y protocoles específicos para los cambios?
What type of virtual or office space is required? | Welk type virtuele ruimte of kantoorruimte is nodig? | Un espace ou bureau spécifique au projet est-il nécessaire ? |  | Che tipo di spazi sono necessari? | ¿Qué tipo de espacio u oficina virtual se requiere?
What else? | En wat verder? | Quoi d'autre ? | Was sonst? | Altro? | ¿Qué más?
Changes | Veranderingen |  |  |  | Cambios
Changes to the Project | Veranderingen in het Project | Autorisation de Changement | Modifikationen der Projektplanung | Autorizzazione delle modifiche | Cambios al Proyecto
Change Authorization | Toestemming tot verandering | Autorisation de Changement |  | Autorizzazione delle modifiche | Autorización de Cambios
Change Authorization Number: | Veranderingsautorisatie nummer: | Autorisation de changement n° | Change-Nummer: | Autorizzazione numero: | Número de Autorización de Cambio
Submitted by: | Ingediend door: | Présenté par : | vorgeschlagen von: | Presentata da: | Elaborado por:
Authorized by: | Geautoriseerd door: | Autorisé par : | Authorisiert durch: | Autorizzata da: | Autorizado por:
Date: | Datum: | Date: | Datum: | Data: | Fecha:
Change Description | Beschrijving verandering | Description des changements : | Änderungsbeschreibung: | Descrizione della modifica: | Descripción del Cambio
Change Impact | Impact van verandering | Impact du changement : | Durch die Änderung betroffen: | Impatto della modifica: | Impacto del Cambio
Change Alternatives Considered | Overwogen alternatieven | Alternatives de changement prises en compte : | Folgende Alternativen wurden berücksichtigt: | Modifiche alternative considerate: | Alternativas de Cambio Consideradas
Anticipated Problems, Implications, Resolution | Verwachte problemen, implicaties, oplossingen: | Résolutions/Problèmes/Questions anticipés | Erwartete Probleme, Hindernisse oder Auswirkungen: | Possibili problemi, implicazioni e soluzioni: | Problemas que se anticipan, implicaciones, solución:
Closeout | Closeout | Clôture | Abschließen | Chiusura | Cierre
Closeout and Evaluate | Closeout and Evaluate | Clôture et Evaluation | Abschließen und bewerten | Chiusura e valutazione | Cierre y Evaluación
Closeout and Evaluate Checklist | Checklist afsluiting en evaluatie | Check-list de Clôture et Evaluation | Abschluß- und Bewertungs-Checkliste | Checklist per chiudere e valutare il progetto | Lista de Verificación para el Cierre y la Evaluación
Deliverables all completed | Alle deliverables gereed | Livrables réalisés | alle Arbeitspakete abgeschlossen | Tutte le attività completate | Todas las realizaciones se terminaron
Contingent actions disabled | Gevolgbestrijdende maatregelen stopgezet | Mesures de secours désactivées | Eventualmassnahmen deaktiviert | Azioni di soccorso disabilitate | Las acciones contingentes se desactivaron
Capitalizing actions disabled | Gevolgbevorderende maatregelen stopgezet | Mesures de capitalisation désactivées | ausschöpfende Massn. Deaktiviert | Azioni di capitalizzazione disabilitate | Las acciones beneficiadoras se desactivaron
Project accounts closed | Project accounts afgesloten | Comptes du projets fermés | alle Projektkonten geschlossen | Doc.economici/finanziari completati | Las cuentas del Proyecto se cerraron
Team members recognized | Teamleden bedankt | Membres de l'équipe reconnus | Team Mitglieder anerkannt | Membri del team congedati | Se dió reconocimiento a los miembros del Equipo
Owners, sponsors, vendors notified of close | Eigenaars, sponsors, en leveranciers geinformeerd | Sponsors, fournisseurs informés de la clôture | Projektgeber, Sponsoren und Vertrieb über Abschluß informiert | Stakeholders, clienti avvisati | Se notificó a los dueños, patrocinadores y proveedores del cierre del proyecto
Results documented | Resultaten gedocumenteerd | Résultats documentés | Resultate documentiert | Risultati documentati | Se documentaron los resultados
Documents archived | Documenten gearchiveerd | Documents archivés | Dokumentation abgeschlossen | Documenti archiviati | Se archivaron los documentos
Did the project satisfy the project statement? If not, explain why. | Voldeed het project aan de projectdefinitie? Zo nee, leg uit waarom niet. | Le projet satisfait-il l'énoncé du projet ? Si non, expliquez pourquoi. | Inwieweit hat das Projekt die Projektbezeichnung erfüllt? Falls nicht, warum? | Il progetto ha soddisfatto l'enunciato? Se no, spiegate perché. | ¿Cumplió el proyecto con el enunciado del proyecto? De no ser así, explicar por qué
How well were project objectives satisfied? How well were customers sponsors, and end users satisfied with the project? If any objectives were not met, explain why. | In hoeverre is aan de projectdoelstellingen voldaan? In hoeverre waren klanten, sponsoren en eindgebruikers tevreden over het project? Als aan bepaalde doelstellingen niet is voldaan, leg uit waarom niet. | A quel point les objectifs du projet ont-ils été satisfaits ? A quel point les clients, sponsors et utilisateurs finaux ont-ils été satisfaits ? Si certains objectifs n'ont pas été atteints, expliquez pourquoi. | Wie gut wurden die Zielsetzungen erfüllt? Wie zufrieden sind Kunden, Sponsoren und Endnutzer mit dem Ergebnis des Projekts? Falls Zielsetzungen nicht erreicht wurden, warum? | Gli obiettivi del progetto sono stati raggiunti in pieno? I clienti e gli stakeholders sono soddisfatti del progetto? Se qualche obiettivo non è stato raggiunto, spiegate perché. | ¿Qué tan bien se cumplieron los objetivos del proyecto? ¿Qué tan satisfechos quedaron los clientes, patrocinadores y usuarios finales con el proyecto? Si algún objetivo no se cumplió, explicar por qué
How well did the project stay on schedule? If any major deliverables were early or late, explain why. How well did the team adjust to schedule changes? | Hoe goed is het project op schema verlopen? Als er belangrijke deliverables te vroeg of te laat klaar waren, leg uit waarom. Hoe goed paste het team zich aan op veranderingen in het schema? | A quel point le projet a-t-il respecté le planning ? Si certains livrables majeurs ont été en avance ou en retard, expliquez pourquoi. L'équipe a-t-elle su s'adapter aux changements ? | Wie gut war das Projekt im Zeitplan? Falls einige Hauptaufgaben zu früh oder zu spät abgeschlossen wurden, warum? Wie gut hat sich das Team Änderungen im Zeitplan angepasst? | La sequenza delle attività è stata rispettata?Se qualche attività è stata svolta in anticipo o in ritardo, spiegate perchè. Il team si è adattato bene a questi cambiamenti? | ¿Qué tan bien cumplió el proyecto con su programación? Si alguna realización mayor se llevó a cabo fuera de tiempo, explicar por qué, ¿Qué tan bien se ajustó el Equipo a los cambios de programación?
How well were resources estimated overall? How did actual use of resources compare to the plan? How did changes in resource availability affect overall implementation? | Hoe goed werden de middelen ingeschat? In hoeverre kwam het feitelijke gebruik van middelen overeen met het plan? In hoeverre hebben veranderingen in de beschikbaarheid van middelen de implementatie beinvloed? | Dans l'ensemble, les ressources ont-elles été bien estimées ? L'utilisation effective des ressources était-elle en accord avec le plan ? De quelle manière les changements de disponibilité des ressources ont-ils affecté la réalisation ? | Wie gut wurde der Ressourcenbedarf geschätzt? Wie hoch ist der Ressourcenverbrauch verglichen mit dem Plan? Wie ging das Team mit Änderungen in der Ressourcenverfügbarkeit um? | Le risorse erano state stimate correttamente? Ci sono differenze fra le risorse impiegate e quelle stimate? I cambiamenti nella disponibilità delle risorse, se ci sono stati, hanno avuto delle ripercussioni sull'esecuzione? | ¿Qué tan bien se estimaron los recursos en su conjunto? ¿Cómo se compara el uso de los recursos con el plan? ¿Los cambios y disponibilidad de recursos afectaron la impementación en su conjunto?
How well did the team work together? How were performance expectations set and maintained? | Hoe goed heeft het team samengewerkt? Hoe zijn de performance verwachtingen gedefinieerd en afgedwongen? | Les membres de l'équipe ont-ils bien travaillé ensemble ? Comment les attentes de performance ont-elles été établies et maintenues ? | Wie gut arbeitete das Team zusammen? | I membri del gruppo hanno lavorato bene insieme? Le aspettative sulla performance sono state soddisfatte? | ¿Qué tan bien hizo su trabano colectivo el Equipo? ¿Cómo se establecieron y mantuvieron las expectativas de desempeño?
How well were performance expectations satisfied during the project? | In hoeverre is tijdens het project aan de performance verwachtingen voldaan? | A quel point les attentes de performance ont-elles été satisfaites ? | Wie gut wurden die Leitungserwartungen während der Implementierung erfüllt? | Durante il progetto le performance attese sono state soddisfatte completamente? | ¿Qué tan bien se cumplieron las expectativas de desempeño durante el desarrollo del proyecto?
What, if any, changes were made to project definition after implementation started? Why? | Welke veranderingen zijn er na aanvang van de implementatie nog aangebracht in de projectdefinitie? Waarom? | Y a-t-il eu des changements à la définition du projet après le début de la réalisation ? Lesquels ? Pourquoi ? | Welche Veränderungen mussten nach Start der Implementierung an der Definition vorgenommen werden und warum? | Ci sono stati dei cambiamenti nella definizione del progetto dopo l'inizio dell'esecuzione? Se si, quali? Perché? | ¿Se hicieron cambios en la definición del proyecto después de haber iniciado la implementación? ¿Por qué sucedió esto?
What, if any, changes were made to the project plan after implementation started? Why? | Welke veranderingen zijn er na aanvang van de implementatie nog aangebracht in de project planning? Waarom? | Y a-t-il eu des changements au plan du projet après le début de la réalisation ? Lesquels ? Pourquoi ? | Welche Modifikationen mussten an der Planung nach Start der Implementierung vorgenommen werden und warum? | Ci sono stati dei cambiamenti nella programmazione del progetto dopo l'inizio dell'esecuzione? Se si, quali? Perché? | ¿Se hicieron cambios en le plan del proyecto después de haber iniciado la implementación? ¿Por qué sucedió esto?
How will you improve the next project you do? | Hoe wilt u uw eerstvolgende project verbeteren? | Comment améliorerez-vous votre prochain projet ? | Was werden Sie beim nächsten Projekt verbessern? | Come migliorereste il vostro prossimo progetto? | ¿Qué haría para mejorar el siguiente proyecto en le que participe?
Summarize the Project | Vat het project samen | Résumé du Projet | Zusammenfassung des Projektes | Riassumere il progetto | Resumen del Proyecto

## Version History (hidden)
Date | Change
2010-12-06 | Creation of this multi-language PMW template from many other templates and KT sources
2011-03-21 | Changes as a result of language reviews included.