## Readme
Kepner-Tregoe Project Management Electronic Worksheets
Purpose
l | Use this electronic version of the Kepner-Tregoe Project Management Worksheets to support small projects.
Intended Use
l | These worksheets are intended to support the use of Kepner-Tregoe's Project Management process.
l | The worksheets contained in this file are not designed to be a substitute for Project Management software.
l | While these worksheets will facilitate the use of Kepner-Tregoe's project management process thinking for smaller projects, we recommend using Microsoft® Project for managing more complex projects.
l | These instructions are not a substitute for an Excel manual or training.
Basic Instructions
l | Complete the "Statement" worksheet first, the "Objectives" worksheet next, followed by the "WBS_RR". Click on the tabs at the bottom of the screen to easily navigate between worksheets.
l | Each worksheet builds on information entered on the previous sheet. Information you are required to enter on each worksheet is shown in a white cell. Information that is automatically generated, either by a calculation or by a previous entry, is shown in a shaded or colored cell.
l | Enter the WBS only in the "WBS_RR" worksheet. WBS columns are stationary in all other worksheets. It will then automatically fill-in the remaining worksheets. Use the slider bar at the bottom of the screen to scroll through the RR and the RAM columns. While entering data, we recommend using the COLUMN: HIDE command to temporarily hide the columns you are not currently working with, so only the current columns are visible. This will facilitate easier data entry. Once your data is entered, use the COLUMN: UNHIDE command to return all columns to their original settings. Use the COLUMN: HIDE/UNHIDE command whenever you want to temporarily remove particular columns from view.
l | Column (insert) To add a column to a worksheet, select the entire column to the right of where you want to insert the new column (Select the entire column by clicking on the column letter [A, B, C, etc.] at the top of the worksheet.) Use the INSERT: COLUMN command to insert an additional column. The new column will be inserted to the left the selected column. Repeat as needed. Tip: Avoid inserting single cells. This may cause particular cells to shift and may produce unexpected results within the worksheet.
l | Column (width): To change the width of a cell, select the entire column by clicking on the column letter at the top of the worksheet. Then, drag the edge of the header cell to the desired width. This will adjust the width of the entire column.
l | Currency: In the Resource Requirements Worksheet, the default currency for the Cost columns is set to dollars ($). To change the currency, selelct the cost cells, go to FORMAT CELLS: NUMBER. You can select the desired currency from the pull down menu titled CURRENCY on the right side of the menu.
l | Delete: To delete data from a cell or group of cells, highlight the cells you want to clear and use the EDIT: CLEAR: CONTENTS command. This will clear the data but retain the worksheet format. It is not recommended to completely delete cells, rows or columns. Doing so may inadvertently cause errors within the worksheet.
l | Notes: Notes in blue describe how to enter information specific to a particular worksheet.
l | Process Questions: To facilitate the use of Kepner-Tregoe Project Management thinking, process questions are embedded next to each process step, indicated by a small red arrow to the right of each process step. To reveal the process questions applicable to a process step, move your mouse over the arrow to the right of the process step.
l | Rows (insert on single worksheet): To add a row to a single worksheet, select the entire row below where you want to insert the new row. (Select the entire row by clicking on the row number at the left of the worksheet.) Use the INSERT: ROW command to insert an additional row. The new row will be inserted above the selected row. Repeat as needed. Tip: Avoid inserting single cells. This may cause particular cells to shift and may produce unexpected results within the worksheet.
l | Rows (insert on multiple worksheets): To add a row to multiple worksheets, "Group" the worksheets in the workbook by holding down the Shift key and clicking on each tab at the bottom of the sheet to which you want the row added. Now, any change you make on one "grouped" sheet will also be made on all the sheets you've selected. Next Insert one or more rows in the location you wish them to appear. Rows will be inserted in all the grouped worksheets.
l | Row (height): To change the height of a cell, select the entire row by clicking on the row number (1, 2, 3, etc.) at the left of the worksheet. Then, drag the edge of the row header cell to the desired height. This will adjust the height of the entire row. Worksheet rows are designed to auto-fit to acommodate the amount of text entered.
l | View: To zoom in or out on the worksheet, use the VIEW: ZOOM command.
For more information on Kepner-Tregoe
Visit our website at www.kepner-tregoe.com
Welcome
Click here to view license terms
!! Use of this worksheet indicates acceptance of license terms !!

## Statement
Please enter project information below. Information entered here will automatically update all the worksheets in this file.
Project Title: | enter title
Project Sponsor: | enter sponsor
Project Manager: | enter project manager
Project Statement:
Created on: | manually enter date created
Last updated on: | manually enter date updated
www.kepner-tregoe.com
Project Statement

## Objectives
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager
Project Statement:
Develop Objectives | Identify Measures | Set Standards
www.kepner-tregoe.com
Project Objectives

## WBS_RR
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager
Project Statement:
|  | Knowledge/Skills |  |  |  | Facilities |  |  |  | Equipment |  |  |  | Materials |  |  |  | Special Resources
WBS Code* | Develop Work Breakdown Structure | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Total
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
* When entering WBS codes, apply style to each cell to format the indent (click format, style, style name dropdown, select 1, 1.1, 1.1.1, etc.)
www.kepner-tregoe.com |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
Work Breakdown Structure
Resource Requirements
Responsibility Assignment Matrix

## RAM
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager |  | Assign Responsibility
Project Statement:
People/Departments
WBS Code | Develop Work Breakdown Structure
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
www.kepner-tregoe.com
Work Breakdown Structure
Resource Requirements
Responsibility Assignment Matrix

## CPM
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager |  | Critical Path Method (CPM) |  |  | Sequence Deliverables (in days) |  |  |  |  | Schedule Deliverables (in calendar time)
Project Statement:
|  |  |  | Critical Path? | Earliest |  | Latest |  |  | Planned |  | Actual
WBS Code | Develop Work Breakdown Structure | Precedence | Duration | (Y/N) | Start | Finish* | Start** | Finish | Slack*** | Start | Finish | Start | Finish | Notes
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
0 | 0 |  |  |  |  | 0 | 0 |  | 0
|  | * Earliest Finish = Earliest Start + Duration |  |  |  | *** Slack = Latest Finish – Earliest Finish
www.kepner-tregoe.com |  | ** Latest Start = Latest finish – Duration
Work Breakdown Structure
Resource Requirements
Sequence and Schedule Deliverables

## Gantt
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager
Project Statement:
|  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
WBS Code | Develop Work Breakdown Structure | Precedence | Duration | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
www.kepner-tregoe.com
Work Breakdown Structure
Resource Requirements
Gantt

## PPA
Last updated on: manually enter date updated
Project Title: enter title |  | Protect the Plan
Project Manager: enter project manager
Project Statement:
WBS Code | Develop Work Breakdown Structure | List Potential Problems | P* | S** | Identify Likely Causes | Take Preventive Action | Plan Contingent Action | Identify Triggers | Steps/Modifications to the Plan | Who | When
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
*P = Probability **S = Seriousness
www.kepner-tregoe.com
Work Breakdown Structure
Resource Requirements
Potential Problem Analysis (PPA)

## POA
Last updated on: manually enter date updated
Project Title: enter title |  | Enhance the Plan
Project Manager: enter project manager
Project Statement:
WBS Code | Develop Work Breakdown Structure | List Potential Opportunities | P* | B** | Identify Likely Causes | Take Promoting Action | Plan Capitalizing Action | Identify Triggers | Steps/Modifications to the Plan | Who | When
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
*P = Probability **B = Benefit
www.kepner-tregoe.com
Resource Requirements
Potential Opportunity Analysis (POA)
Work Breakdown Structure

## Implement
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager
Project Statement:
Start to Implement Checklist
What type of formal project kickoff meeting is required?
What other communication about the initiation of work might be required or useful?
What documentation might be useful or necessary during any kickoff communications?
What ground rules will be necessary for the entire team, or subgroups of the team, to operate efficiently?
Are specific policies or protocols for changes required?
What type of virtual or office space is required?
What else?
www.kepner-tregoe.com
Start to Implement
Individual and/or group communications planned
Project documentation assembled to guide implementation
Materials, facilities, equipment, funding, etc., in place for initial tasks
Ground rules established for team interaction, communication
Potential Problem/Opportunity Analysis done for critical initial tasks
Team and team member performance systems agreed to and in place
Monitoring systems and methods agreed to
and in place
Issue resolution protocols agreed to and in place
Reporting systems and methods agreed to
and in place
Change control systems agreed to and in place
Check Box -1002
Check Box -1001
Check Box -1000
Check Box -999
Check Box -998
Check Box -997
Check Box -996
Check Box -995
Check Box -994
Check Box -993

## Change Auth.
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager
Project Statement:
Change Description:
Change Impact:
Change Alternatives Considered:
Anticipated Problems, Implications, Resolution:
www.kepner-tregoe.com
Change Authorization
Change Authorization Number:
Submitted by: Date:
Authorized by: Date:

## Closeout
Last updated on: manually enter date updated
Project Title: enter title
Project Manager: enter project manager
Project Statement:
Closeout and Evaluate Checklist | Summarize the Project
Did the project satisfy the project statement? If not, explain why.
How well were project objectives satisfied? How well were customers, sponsors, and end users satisfied with the project? If any objectives were not met, explain why.
How well did the project stay on schedule? If any major deliverables were early or late, explain why. How well did the team adjust to schedule changes?
How well were resources estimated overall? How did actual use of resources compare to the plan? How did changes in resource availability affect overall implementation?
How well did the team work together? How were performance expectations set and maintained?
How well were performance expectations satisfied during the project?
What, if any, changes were made to project definition after implementation started? Why?
What, if any, changes were made to the project plan after implementation started? Why?
How will you improve the next project you do?
www.kepner-tregoe.com
Closeout and Evaluate
Deliverables all completed
Contingent actions disabled
Capitalizing actions disabled
Project accounts closed
Team members recognized
Owners, sponsors, vendors notified of close
Results documented
Documents archived
Check Box -1021
Check Box -1020
Check Box -1019
Check Box -1018
Check Box -1017
Check Box -1016
Check Box -1014

## License
TEMPLATE LICENSE AGREEMENT
PLEASE READ THIS LICENSE CAREFULLY BEFORE USING THE KEPNER-TREGOE(R) TEMPLATES/WORKSHEETS (“TEMPLATES”). BY INSTALLING OR USING THE TEMPLATES YOU ARE AGREEING TO BE BOUND BY THE TERMS OF THIS LICENSE.
GENERAL. Except as authorized below, the Templates may not, in whole or in part, be used, copied, photocopied, printed, reproduced, translated or reduced to any electronic without prior written consent from Kepner-Tregoe, Inc. (“KT”).
LICENSE. KT hereby grants you a nonexclusive and nontransferable license to print, reproduce and use the Templates in Microsoft(R) Excel format under the following terms and conditions:
1. You are not permitted to modify or alter the format of the Templates in any way without KT’s written permission.
2. This license is only granted to you if you have been trained in a KT approved program of Project Management and received a purchased set of KT Project Management workshop materials.
3. The KT copyright legend must remain on all screen and print copies of the Templates.
4. The Templates cannot be downloaded, transferred to or accessed by others unless such individuals agree to
the terms of this License and are specifically eligible to use the Templates under Subsection 2 above.
5. The Templates shall not be used in conjunction with or as a part of any software that prompts the user to
complete the Templates. The limited purpose of this license is to allow you to store the Templates in electronic
form in place of or in addition to paper copies and to allow electronic access to and storage of completed forms.
TERMINATION. This License is effective until terminated. You may terminate this License at any time by destroying the Templates and all copies thereof. This License will terminate immediately without notice from KT if you fail to comply
with any provision of this License. Upon termination you must destroy all copies of the Templates.
GOVERNMENT END-USERS. If you are acquiring the Templates on behalf of any unit or agency of the United States Government, the following provisions apply. The Government agrees: (1) If the Templates are supplied to the Department of Defense (DoD), the Templates are classified as “Commercial Computer Software” and the Government is acquiring only “restricted rights” in the Templates as that term is defined in Clause 252.227-7013(c)(1) of the DFARS; and (2) If the Templates are supplied to any unit or agency of the United States Government other than DoD, the Government’s rights in the Templates will be as defined in Clause 52.227-19(c)(2) of the FAR or, in the case of NASA, in Clause 18-52.227-86(d) of the NASA Supplement to the FAR.
DISCLAIMER OF WARRANTY ON TEMPLATES. You expressly acknowledge and agree that use of the Templates is at your sole risk. The Templates are provided “AS IS” and without warranty of any kind and KT EXPRESSLY DISCLAIMS ALL WARRANTIES, EXPRESS AND IMPLIED, INCLUDING, BUT NOT LIMITED TO, THE IMPLIED WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR PURPOSE. FURTHERMORE, KT DOES NOT WARRANT OR MAKE ANY REPRESENTATIONS REGARDING THE USE OR THE RESULTS OF THE USE OF THE TEMPLATES IN TERMS OF THEIR CORRECTNESS, ACCURACY, RELIABILITY, CURRENTNESS, OR OTHERWISE. SOME JURISDICTIONS DO NOT ALLOW THE EXCLUSION OF IMPLIED WARRANTIES, SO THE ABOVE EXCLUSION MAY NOT APPLY TO YOU.
LIMITATION OF LIABILITY. UNDER NO CIRCUMSTANCES INCLUDING NEGLIGENCE, SHALL KT BE LIABLE TO YOU FOR ANY INCIDENTAL, INDIRECT, SPECIAL OR CONSEQUENTIAL ARISING OUT OF THE USE, MISUSE OR INABILITY TO USE THE TEMPLATES, EVEN IF KT OR KT’S AUTHORIZED REPRESENTATIVE HAS BEEN ADVISED OF THE POSSIBILITY OF SUCH DAMAGES. SOME JURISDICTIONS DO NOT ALLOW THE LIMITATION OR EXCLUSION OF LIABILITY FOR INCIDENTAL OR CONSEQUENTIAL DAMAGES, SO THE ABOVE LIMITATION OR EXCLUSION MAY NOT APPLY TO YOU.
CONTROLLING LAW AND SEVERABILITY. This License shall be governed by and construed in accordance with the laws of the United States and the State of New Jersey. If for any reason a court of competent jurisdiction finds any provision of this License or portion thereof, to be unenforceable, that provision of the License shall be enforced to the maximum extent permissible so as to effect the intent of the parties, and the remainder of this License shall continue in full force and effect.
COMPLETE AGREEMENT. This License constitutes the entire agreement between the parties with respect to the use of the Templates and supersedes all prior or contemporaneous understandings or agreements, written or oral, regarding such subject matter. No amendment to or modification of this License will be binding unless in writing and signed by a duly authorized representative of KT.